## Sheet1
	Issues	Count
	Open	8
	Reopen	0
	Closed	0
	Total	8
					IGOTEVENT

			TESTING : IGOTEVENT CREATED BY :Ashima Sharma(QA)
S.No.	Issue Title	Description	Type of User	Device	Priority	Issue Type	Issue Raised Date	Issue Closed Date	Status By Developer	Status By QA	Developer's Comment	QA Comments
1	Post Job	User should not take start date as previous date.	Client	android	High	Functionality	12/07/17			Open
2	Forgot password	When user update password through link then it moves to website. After updating password user should not move to website sign up screen.	Client/ESP	Android/IOS	High	Functionality	12/07/17			Open
3	In app	Double Alerts are shown in all text field. Alert should be displayed single time.	Client/ESP	Android/IOS	High	Functionality	12/07/17			Open
4	Title	user should not allow to enter smiley's on title.	ESP	ios	High	Functionality	12/07/17			Open
5	Sign Up/Edit Profile	user should not allow to enter smiley's , Special character and number in first and last name field.	Client/ESP	Android/IOS	High	Functionality	12/07/17			Open
6	Post Job	Random crash occur when user post new job.	ESP	ios	High	blocker	12/07/17			Open
7	Post Job	There should be “Your job updated successfully” instead of “your job was updated”.	ESP	ios	High	Functionality	12/07/17			Open
8	Post Job	When user post job then there is double alert shown.	ESP	ios	High	Functionality	12/07/17			Open
9
10