## Merchants
| Status By Developer | Cases
| Open | 28
| Reopen | 0
| Closed | 1
| Total | 29 |  |  | Trusted Services (Merchant)
TESTING : Trusted Services(iOS) CREATED BY: Ashima Sharma(QA)
S.No. | Issue Title | Description | Android /IOS | Priority | Issue Type | Issue Raised Date | Issue Closed Date | Status By Developer | Status By QA | Developer's Comment | QA Comments
1 | Create profile | upload picture icon is stretched | iOS | High | GUI | 22/3/2017 |  |  | Open | Pending
2 | Create profile | Uploaded Pics are showing as stretched | iOS | High | Functionality | 22/3/2017 |  |  | Open | Pending
3 | sign up | There should be email in hint instead of Email Address | iOS | High | GUI | 24/3/17 |  | Fixed | Open
4 | Login | There should be email in hint instead of Email Address | iOS | High | GUI | 24/3/17 |  | Fixed | Open
5 | Forgot password | There should be email in hint instead of Email Address | iOS | High | GUI | 24/3/17 |  | Fixed | Open
6 | Login | There should be Don't have an Account yet? Instead of Don't have an account | iOS | High | GUI | 24/3/17 |  | Fixed | Open
7 | App icon | the text Athena Merchant is not completely visible | iOS | High | GUI | 24/3/17 |  |  | Open | This is the iOS enviorment if the name of the app is long it will truncate.
8 | Tell us About Your Business | The heading is not completely visible | iOS | High | GUI | 24/3/17 |  | Fixed | Open
9 | Login with fb | When we enter business information through merchant side the message is displayed the customer can't add business information | iOS | High | Functionality | 24/3/17 |  | Fixed | Open
10 | Home | The ui of home screen is not match with android There is extra text displayed Your next Upcoming Service, it should only display when the new sevice is come and there is message in android No upcoming Service, but in ios there is No Next Service Yet. | iOS | High | GUI | 24/3/17 |  | Fixed | Open
11 | Previous booking | Match the screen ui with Android | iOS | High | GUI | 24/3/17 |  | Fixed | Open
12 | Profile | business Information is missing | iOS | High | GUI | 24/3/17 |  |  | Open
13 | Profile | Change Password, Change Mobile No. and My services all are in capital | iOS | High | GUI | 24/3/17 |  | Fixed | Open
14 | profile | The Business name is shown above on rating in android | iOS | High | GUI | 24/3/17 |  |  | Open | This is service name it will show below the raring
15 | Edit Profile | There should be option for edit business information in android but not in iOS | iOS | High | GUI | 24/3/17 |  | Pending | Open
16 | Change Mobile no | The +254 usd code is missing from Phone number field | iOS | High | GUI | 24/3/17 |  | Fixed | Open
17 | select your services | In this last service trimming the cross icon is cut from bottom | iOS | High | GUI | 24/3/17 |  |  | Open | Not Found. Please check it again if there is any issue then please take a screen short.
18 | Profile | Ui of Profile is incorrect check screen shot inBlack ipod | iOS | High | GUI | 24/3/17 |  | Fixed | Open
19 | Select Your Services | when click on enter manually pop up displayed and the ui is shown incorrect the yellow circle is shown in below of the screen screen shot inBlack ipod | iOS | High | GUI | 24/3/17 |  | Fixed | Open
20 | Profile | when click on enter manually pop up displayed and the ui is shown incorrect the yellow circle is on profile when we come back from select Services screen it is shown in below of the screen screen shot inBlack ipod | iOS | High | GUI | 24/3/17 |  | Fixed | Open
21 | In app | in all app the yellow circle is shown botton of every screen | iOS | High | GUI | 24/3/17 |  | Fixed | Open
22 | Settings | When Notifications off notification come there should be funtionality that when notifications on only then notifications come | iOS | High | Functionality | 24/3/17 |  |  | Open | Dependency on backend
23 | Settings | About us is not working | iOS | High | Functionality | 24/3/17 |  | Not Implemented yet. | Open
24 | Settings | Privacy policy is not wiorking | iOS | High | Functionality | 24/3/17 |  | Not Implemented yet. | Open
25 | Settings | Terms and conditions are not working | iOS | High | Functionality | 24/3/17 |  | Not Implemented yet. | Open
26 | Settings | Help center is not working | iOS | High | Functionality | 24/3/17 |  | Not Implemented yet. | Open
27 | Service Receipt | Notification sound come but notification not shown | iOS | High | Functionality | 24/3/17 |  | Fixed | Open
28 | Rate your customer | The two stars are already filled | iOS | High | Functionality | 24/3/17 |  | Fixed | Open
29 | Session expire | Same user is login on two devices no session expire message is display. E.g Abc as merchant login in iOs and xyz Customer login in ios and same as android then when payment receive and Make Payment is come then the notification is come on same devices | iOS | High | Functionality | 24/3/17 |  | Fixed | Closed |  | Blocker

## Customer
| Status By Developer | Cases
| Open | 27
| Reopen | 0
| Closed | 4
| Total | 31 |  |  | Trusted Services (Customer)
TESTING : Trusted Services(iOS) CREATED BY: Ashima Sharma(QA)
S.No. | Issue Title | Description | Android /IOS | Priority | Issue Type | Issue Raised Date | Issue Closed Date | Status By Developer | Status By QA | Developer's Comment | QA Comments
1 | Create profile | upload picture icon is stretched | iOS | High | GUI | 24/3/17 |  |  | Open
2 | Home | Alex barber's location is not completely visible | iOS | High | GUI | 24/3/17 |  | Fixed | Closed
3 | Home | When click on merchant's profile there should not be space b/w name, profession and location | iOS | High | GUI | 24/3/17 |  | Fixed | Closed
4 | Home | When click on View Profile of merchant then below location There should be Occupation displayed | iOS | High | Functionality | 24/3/17 |  |  | Open | Occupation display on the navigation bar
5 | Book now | There should be select services instead of Select merchant Services | iOS | High | GUI | 24/3/17 |  | Fixed | Closed
6 | Services | when we click on any Services on view profile Random crash occur | iOS | High | Functionality | 24/3/17 |  | Fixed |  | Back End | Crash
7 | Services | When We click on any Services on book now Random crash occur | iOS | High | Functionality | 24/3/17 |  | Fixed | Open | Back End | Crash
8 | Select Services | Filter is not working | iOS | High | Functionality | 24/3/17 |  | Fixed | Open | Back End
9 | Services | When we click on any services no information is shown only rating and profile pic icon is display no data is shown | iOS | High | Functionality | 24/3/17 |  | Fixed | Open
10 | Services | When we are on Services screeen it is display Home as Heading It should be Services | iOS | High | GUI | 24/3/17 |  | Fixed | Open
11 | My Bookings | Upcoming Bookings and Previous Bookings should be in capital letters | iOS | High | GUI | 24/3/17 |  |  | Open | This is as such as in UI design
12 | Profile | The Change Password text should be in capital letters | iOS | High | GUI | 24/3/17 |  | Fixed | Open
13 | Profile | Change Mobile no should be in capital letters | iOS | High | GUI | 24/3/17 |  | Fixed | Open
14 | Profile | The Profile Screen UI ias not correct the Screen shot available in black ipod | iOS | High | GUI | 24/3/17 |  |  | Open
15 | Settings | When Notifications off notification come there should be funtionality that when notifications on only then notifications come | iOS | High | Functionality | 24/3/17 |  |  | Open | Back End Dependency
16 | Settings | About us is not working | iOS | High | Functionality | 24/3/17 |  | Not Implemented yet. | Open
17 | Settings | Privacy policy is not wiorking | iOS | High | Functionality | 24/3/17 |  | Not Implemented yet. | Open
18 | Settings | Terms and conditions are not working | iOS | High | Functionality | 24/3/17 |  | Not Implemented yet. | Open
19 | Settings | Help center is not working | iOS | High | Functionality | 24/3/17 |  | Not Implemented yet. | Open
20 | Favorite | The Profile of favorites is not clickable and no View Profile and book now option is there | iOS | High | Functionality | 24/3/17 |  | Fixed | Open
21 | My cards | In android there is no option show whether the card is visa or master on main listing | iOS | High | GUI | 24/3/17 |  |  | Open | On iOS side that is OK
22 | My booking | When click on 1 or 2 More the popup is open please match with android | iOS | High | GUI | 24/3/17 |  |  | Open
23 | Profile | When we click on edit there is rating shown which is not shown in android match with android | iOS | High | GUI | 24/3/17 |  |  | Open
24 | sign up | There should be email in hint instead of Email Address | iOS | High | GUI | 24/3/17 |  | Fixed | Open
25 | Login | There should be email in hint instead of Email Address | iOS | High | GUI | 24/3/17 |  | Fixed | Open
26 | Forgot password | There should be email in hint instead of Email Address | iOS | High | GUI | 24/3/17 |  | Fixed | Open
27 | Login | There should be Don't have an Account yet? Instead of Don't have an account | iOS | High | GUI | 24/3/17 |  | Fixed | Open
28 | Home | There is nairobi kenya location in filter but on home screen cleaner is shown from thika, kenya | iOS | High | Functionality | 24/3/17 |  |  | Open | There is radius funcatnalty up do 50 miles
29 | Service Receipt | When user make payment once he or she can't click on make payment again and again for same job | ios | High | Functionality | 24/3/17 |  | Fixed | Open | if user did't recived notification then what we have to do?
30 | Home | Many time I select nairobi as location but it shows city parliament all times | ios | High | Functionality | 24/3/17 |  |  | Open | When user will come on home screen first time it will fetch user current location
31 | Home | There should be option for search services according to current location | ios | High | Functionality | 24/3/17 |  |  | Open | Location Icon will fetch current location.
32 | Session expire | Same user is login on two devices no session expire message is display. E.g Abc as merchant login in iOs and xyz Customer login in ios and same as android then when payment receive and Make Payment is come then the notification is come on same devices | iOS | High | Functionality | 24/3/17 |  | Fixed | Closed |  | Blocker