## Sheet1
| Status By Developer | Cases
| Open | 29
| Reopen | 0
| Closed | 2
| Total | 31 |  |  | Trusted Services (Merchant)
TESTING : Trusted Services(Android) CREATED BY: Ashima Sharma(QA)
S.No. | Issue Title | Description | Android /IOS | Priority | Issue Type | Issue Raised Date | Issue Closed Date | Status By Developer | Status By QA | Developer's Comment | QA Comments
1 | App icon | The merchant is not completely visible… | Android | High | Gui | 23/3/17 |  | Done | Open
2 | Sign up | there is hint of Email in ui design instead of Emil Address | Android | High | Gui | 23/3/17 |  | Done | Open
3 | Sign up | There should be Re-Password instea of Confirm Password | Android | High | Gui | 23/3/17 |  | Done | Open
4 | Sign up | The Color of Terms and Conditions should be black not blue | Android | High | Gui | 23/3/17 |  | Done | Open
5 | Sign up | Create Account button should be wide as according to ui | Android | High | Gui | 23/3/17 |  | Done | Open
6 | Sign up | there should be Already have an Account? instead of Already have an Account yet? | Android | High | Gui | 23/3/17 |  | Done | Open
7 | Sign up | When we press back on Register it should navigates to login screen rather than close the app | Android | High | Gui | 23/3/17 |  | Done | Open
8 | Login | In Login Screen there should be no back button and text should be in middle that is Login With Your Email and no question mark sign is needed there | Android | High | Gui | 23/3/17 |  | Done | Open
9 | Navigation menu | The Name of items should be in capital letter according to ui | Android | High | Gui | 23/3/17 |  | Done | Open
10 | Menu>New Request | There should be New Request instead of Request and icon of NEW REQUEST should be change | Android | High | Gui | 23/3/17 |  | Done | Open
11 | Menu>PAYMENT | There should be PAYMENTS instead of PAYMENT | Android | High | Gui | 23/3/17 |  | Done | Open
12 | Notification | There should be NOTIFICATIONS instead of Notification | Android | High | Gui | 23/3/17 |  | Done | Open
13 | Profile | Profile pic of victor smith is not shown Screen shot available in Nexus | Android | High | Functionality | 23/3/17 |  | done | Open
14 | Rating | After receive payment when user give rating and after submit there is grey screen open Screen shot available in Nexus | Android | High | Functionality | 23/3/17 |  | Done | Closed
15 | Profile | Edit Services should be My Services | Android | High | Gui | 23/3/17 |  | Done | Open
16 | Payment | If user receive payment once then there should be alert message shown and second time it is not receive the payment for same task | Android | High | Functionality | 23/3/17 |  | Done | Open | Dependency on Backend
17 | Edit Profile | Location icon is not correct, | Android | High | Gui | 23/3/17 |  | Done | Open
18 | login with Fb | Login with fb is not working | Android | High | Functionality | 24/3/17 |  |  | Open | Dependency on Backend
19 | Home | When Upcoming Service is come then there is time which is in red color in iOS | Android | High | Gui | 24/3/17 |  | Done | Open
20 | My Bookings | When Upcoming Service is come then there is time which is in red color in iOS | Android | High | Gui | 24/3/17 |  | Done | Open
21 | My services | when click on my Services there should be heading of Select Your services instead of My services | Android | High | Gui | 24/3/17 |  | Done | Open
22 | My services | When click on Enter Manually no pop up is open while in iOS there is pop up message displayed | Android | High | Functionality | 24/3/17 |  | Done | Open
23 | Settings | When Notifications off notification come there should be funtionality that when notifications on only then notifications come | Android | High | Functionality | 24/3/17 |  | Not Implemented | Open | No Detail found from PM
24 | Settings | About us is not working | Android | High | Functionality | 24/3/17 |  | Not Implemented | Open | No Detail found from PM
25 | Settings | Privacy policy is not wiorking | Android | High | Functionality | 24/3/17 |  | Not Implemented | Open | No Detail found from PM
26 | Settings | Terms and conditions are not working | Android | High | Functionality | 24/3/17 |  | Not Implemented | Open | No Detail found from PM
27 | Settings | Help center is not working | Android | High | Functionality | 24/3/17 |  | Not Implemented | Open | No Detail found from PM
28 | Upcoming bookings | The time is in red color in iOs | Android | High | Gui | 24/3/17 |  | Not Implemented | Open
29 | Previous Booking | Match the UI with iOS | Android | High | Gui | 24/3/17 |  | Not Implemented | Open
30 | Service receipt | The Total is Total Price : in iOS and there should be Ksh instead od $ | Android | High | Gui | 24/3/17 |  | Done | Open
31 | Session expire | Same user is login on two devices no session expire message is display. E.g Abc as merchant login in iOs and xyz Customer login in ios and same as android then when payment receive and Make Payment is come then the notification is come on same devices | Android | High | Functionality | 24/3/17 |  | Done | Closed |  | Blocker

## Sheet2
| Status By Developer | Cases
| Open | 41
| Reopen | 0
| Closed | 1
| Total | 42 |  |  | Trusted Services (Customer)
TESTING : Trusted Services(Android) CREATED BY: Ashima Sharma(QA)
S.No. | Issue Title | Description | Android /IOS | Priority | Issue Type | Issue Raised Date | Issue Closed Date | Status By Developer | Status By QA | Developer's Comment | QA Comments
1 | Home | There is text No Provider Found instead of this there should be message No Service Provider Found and it should be in center of screen | Android | High | Gui | 23/3/17 |  | Done | Open
2 | Home | Location is not completely visible ….are shown | Android | High | Gui | 23/3/17 |  |  | Open | One liner address
3 | Sign up | there is hint of Email in ui design instead of Emil Address | Android | High | Gui | 23/3/17 |  | Done | Open
4 | Sign up | There should be Re-Password instea of Confirm Password | Android | High | Gui | 23/3/17 |  | Done | Open
5 | Sign up | The Color of Terms and Conditions should be black not blue | Android | High | Gui | 23/3/17 |  | Done | Open
6 | Sign up | Create Account button should be wide as according to ui | Android | High | Gui | 23/3/17 |  | Done | Open
7 | Sign up | there should be Already have an Account? instead of Already have an Account yet? | Android | High | Gui | 23/3/17 |  | Done | Open
8 | Sign up | When we press back on Register it should navigates to login screen rather than close the app | Android | High | Functionality | 23/3/17 |  | Done | Open
9 | Login | In Login Screen there should be no back button and text should be in middle that is Login With Your Email and no question mark sign is needed there | Android | High | Functionality | 23/3/17 |  | Done | Open
10 | Payment | When user make payment once he or she can't click on make payment again and again for same job | Android | High | Functionality | 23/3/17 |  | Done | Open
11 | Navigation menu | The Name of items should be in capital letter according to ui | Android | High | Gui | 23/3/17 |  | Done | Open
12 | Menu>PAYMENTS | There should be PAYMENTS instead of PAYMENT | Android | High | Gui | 23/3/17 |  | Done | Open
13 | Notifications | There should be NOTIFICATIONS instead of Notification | Android | High | Gui | 23/3/17 |  | Done | Open
14 | My Bookings | There should be My Bookings instead of My Booking and it should be in Capital | Android | High | Gui | 23/3/17 |  | Done | Open
15 | Home | There is Service Type instead of Select Services | Android | High | Gui | 23/3/17 |  | Done | Open
16 | Home | There is Within 0 KSH instead of within ksh 0 | Android | High | Gui | 23/3/17 |  | Done | Open
17 | Home | There should be Within 2000 KSH instead of within ksh 2000 | Android | High | Gui | 23/3/17 |  | Done | Open
18 | Home | In iOS Name of Merchant is shown intead of business name | Android | High | Gui | 23/3/17 |  | Done | Open
19 | Home | Alex salon the location address is not completely visible | Android | High | Gui | 23/3/17 |  |  | Open | One line in Ui
20 | Home | The business Name should be in capital letters e.g-> Barber, Stephen Cleaner Ltd | Android | High | Gui | 23/3/17 |  | Done | Open
21 | Home | When we click on any merchant the text pricing is missing from the profile of Merchant where pricing list is shown | Android | High | Gui | 23/3/17 |  | Done | Open
22 | Select Services | In Select Services The Pricing detail should be in red color same as ios | Android | High | Gui | 23/3/17 |  | Done | Open
23 | Book Now | When we are click for advance booking user can and today's date and past time for advance booking which is incorrect | Android | High | Functionality | 23/3/17 |  | Done | Open | Dependency on backend
24 | services | When we click on any of services like barber, chef no listing and information is shown | Android | High | Functionality | 23/3/17 |  | Done | Open
25 | Select Services | filter is not working | Android | High | Functionality | 23/3/17 |  | Done | Open
26 | Services | All The services should be in capital letters as it is in iOS | Android | High | Functionality | 24/3/17 |  | Done | Open
27 | Settings | When Notifications off notification come there should be funtionality that when notifications on only then notifications come | Android | High | Functionality | 24/3/17 |  | Not Implemented yet | Open
28 | Settings | About us is not working | Android | High | Functionality | 24/3/17 |  | Not Implemented yet | Open
29 | Settings | Privacy policy is not wiorking | Android | High | Functionality | 24/3/17 |  | Not Implemented yet | Open
30 | Settings | Terms and conditions are not working | Android | High | Functionality | 24/3/17 |  | Not Implemented yet | Open
31 | Settings | Help center is not working | Android | High | Functionality | 24/3/17 |  | Not Implemented yet | Open
32 | Favorites | There is profile of favorites that is not clickable | Android | High | Functionality | 24/3/17 |  | Done | Open
33 | My Cards | In ios there is option showsz whether the card is Visa or master match ui with ios | Android | High | Gui | 24/3/17 |  | Done | Open
34 | My Bookings | When click on 1 or 2 More the popup is open please match with iOS | Android | High | Gui | 24/3/17 |  | Done | Open
35 | Profile | when we click on save after edit the profile pop is displayed the Profile updated successfully | Android | High | Gui | 24/3/17 |  | Done | Open
36 | Service Receipt | when customer is on service Receipt and there is Total Price in iOS and there should be Ksh instead of $ sign | Android | High | Gui | 24/3/17 |  | Done | Open
37 | Home | There is nairobi kenya location in filter but on home screen cleaner is shown from thika, kenya | Android | High | Functionality | 24/3/17 |  |  | Open | Backend Issue
38 | My bookings | When click on My booking after notification random crash occur | Android | High | Functionality | 24/3/17 |  |  | Open |  | Crash
39 | Service Receipt | Heading of SERVICE RECIEPT is in capital in iOs | Android | High | Gui | 24/3/17 |  | Done | Open
40 | Notifications | When nmerchant accept the request no notification are shown or received | Android | High | Functionality | 24/3/17 |  |  | Open | Backend Issue
41 | Home | Many time I select nairobi as location but it shows city parliament all times | Android | High | Functionality | 24/3/17 |  |  | Open | Backend Issue
42 | Session expire | Same user is login on two devices no session expire message is display. E.g Abc as merchant login in iOs and xyz Customer login in ios and same as android then when payment receive and Make Payment is come then the notification is come on same devices | Android | High | Functionality | 24/3/17 |  | Done | Closed |  | Blocker