## Sheet1
	Issue Status	Count		Priority	Count
	Open	17		Blocker	0
	Reopen	0		High	12
	Repeated	0		Medium	4
	Closed	0		Low	1
	Total	17

			TESTING :Millionaires (Service Provider) Android
S.NO	Issue Title	Description	Priority	Device	Issue Type	Status By QA	Issue Raised Date	Issue Closed Date	Status By Developer

1	Register	Name of the field is Usename where as alert is showing Please enter name, please make it “Please enter username”. And remove the space from Username same as UI.	medium	android	gui(both side)	open	mantis
	Register	Username field should accept special characters.	high	android	functionality(both side)	open	mantis
	Register	If password and re-password match, alert is shown Confirm password not match. Alert should be same as field placeholder or itsw name. Please make alert “Password and Re-Password doesn’t match.”	medium	android	gui(both side)	open	mantis
	Register	Once user register successfully, user should be navigated to create profile instead of login screen. And user need to login in order to proceed further.	high	android	functionality(both side)	open	mantis
	Login	1) If user enter email id that is not registered in application, Alert is shown Email not found, please make it “Email doesn’ exist, Please register first.” Same goes for forgot password screen. / 2) For password, please make alert: Password is not valid, please enter correct password.	medium	android	gui(both side)	open	mantis
	Forgot password	Its not working, it keeps showing email not found even if user enter the registered email Id.	high	android	functionality(both side)	open	mantis
	Forgot password	When user click on anywhere in screen keyboard should get closed.	high	android	functionality(both side)	open	mantis
	create profile	If user press back button on create profile screen, user is navigated to Millionairess network screen. User should not be able to go back from create profile screen.	high	android	functionality(both side)	open	mantis
	create profile	If user enter only blank space in all fields, error maeesge is shown Undefined method “each” for “[\”7\]”: String. And user is not able to create profile.	high	android	functionality	open	mantis
	create profile	Keyboard should get closed if user scroll up or down screen. Eg: User is on qualification field and when user scroll up, keyboard should get closed.	high	android	functionality	open	mantis
	Login	1) Email address should not be case sesitive. / 2) If user is entering email id registered in customer side in service provider side, it should show alert “This email address is already registered in customer side, please use other email.”	high	android	functionality	open	mantis
	Home	Please increase the size of availability toggle.	medium	android	gui	open	mantis
	Rating	If user has no rating, message is shown No user found, Please make it “You haven’t recieved any rating so far”.	low	android	gui	open	mantis
	Settings>notification	If user turn off notification toggle and user goes on other screen say home and come back on settigns screen, notification toggle turned on.	high	android	functionality	open
	settings>chnage password	If user has logged in from social media account, option to change password should not be there.	high	android	functionality	open	mantis
	Edit profile	User is not able to edit profile, it keeps sending error message.	high	android	functionality	open	mantis
	Naivgation bar	When user click on profile, screen is appeared backside, user need to scroll navigation bar to left side inorder to check profile.	high	android	functionality	open	mantis